## Read me
SmartBiz Estate: end-to-end process test script (Sprints 0-10)
Walks a landlord, an agency and a developer through the whole system in business order, so later steps build on earlier ones.
Before you start
1. Fresh database | Demo dates are relative to the day the data is seeded. Start from a clean database so expected values match: dotnet ef database drop --force --project src/RealEstateERP.Infrastructure --startup-project src/RealEstateERP.Web
2. Run in Development | dotnet run --project src/RealEstateERP.Web Migrations are applied and demo data is seeded on first start.
3. Email | Without SMTP, every email lands in the dev mailbox at /dev/mailbox. With SMTP (Admin > Settings > Email), use addresses you can open.
4. Order | Run the steps top to bottom. Development costing (S9b) comes before Sales (S9) so its demo numbers hold.
5. Credits | Some steps use credits (PDFs, leads, invoice runs). If a business runs low, top it up via superadmin (Admin > Credit purchases > adjust).
Demo accounts (password for all: Demo@12345)
superadmin@smartbiz.test | Platform admin: payment approvals, plans, settings, users, businesses
owner@smartbiz.test | Owns Acacia Gardens (landlord) and Savanna Homes (developer, plot sales)
admin@smartbiz.test | Admin at Acacia Gardens
staff@smartbiz.test | User at Acacia Gardens (can edit, can't renew or manage team)
viewer@smartbiz.test | Viewer at Acacia Gardens (read-only)
agent@smartbiz.test | Principal of Mji Property Agents (agency)
james@smartbiz.test | Agent at Mji Property Agents: sees only his own contracts and sales
lapsed@smartbiz.test | Owns Lapsed Holdings: suspended, payment awaiting approval
newuser@smartbiz.test | No business yet
How to record results
Cells you fill in | Only the shaded columns on 'Test script': Status, Actual result / notes, Tester, Date. Everything else is the script.
Status | Pick from the list: Not run, Pass, Fail, Blocked. 'Blocked' = couldn't run because an earlier step failed.
Fail | Write what actually happened in 'Actual result / notes', then log it on 'Defects' with the test ID. The example row there shows the format.
Summary | Counts and pass rate per sprint update automatically from the Status column.

## Summary
Results by sprint
Updates automatically from the Status column on 'Test script'. Pass rate = Pass / (steps run).
Sprint | Steps | Pass | Fail | Blocked | Not run | Run | Pass rate
S0 Foundation | 11 | 0 | 0 | 0 | 11 | 0 | -
S1 Subscriptions | 8 | 0 | 0 | 0 | 8 | 0 | -
S2 Portfolio | 7 | 0 | 0 | 0 | 7 | 0 | -
S3 Tenants and leases | 9 | 0 | 0 | 0 | 9 | 0 | -
S4 Billing | 8 | 0 | 0 | 0 | 8 | 0 | -
S5 Collections | 9 | 0 | 0 | 0 | 9 | 0 | -
S6 Arrears, credits, PDFs | 8 | 0 | 0 | 0 | 8 | 0 | -
S7 Accounts and admin | 16 | 0 | 0 | 0 | 16 | 0 | -
S8 Agency | 14 | 0 | 0 | 0 | 14 | 0 | -
S9b Development costing | 10 | 0 | 0 | 0 | 10 | 0 | -
S9 Sales | 15 | 0 | 0 | 0 | 15 | 0 | -
S10 Marketplace | 13 | 0 | 0 | 0 | 13 | 0 | -
X Cross-cutting | 4 | 0 | 0 | 0 | 4 | 0 | -
Total | 132 | 0 | 0 | 0 | 132 | 0 | -
Open defects | 0

## Test script
ID | Sprint | Area | Sign in as | Steps | Test data | Expected result | Status | Actual result / notes | Tester | Date
F-01 | S0 Foundation | Public site | Signed out | Open the home page. Click Features, Pricing, About, Contact and Find a property. | - | Hero reads 'Rentals and plot sales, without the paperwork'. Every page loads in the navy/amber design. Pricing shows the 4 plans from the database. | Not run
F-02 | S0 Foundation | Sign in | Signed out | Open Sign in. Click a demo account email in the demo panel. | - | The email fills in. Demo password and a link to the dev mailbox are shown (Development only). Show/hide password works. | Not run
F-03 | S0 Foundation | Register | Signed out | Click Create an account. Enter full name, email, password, tick the terms. Submit. | Name: QA Tester; your own email (or qa1@smartbiz.test); password Qa@123456 | 'Check your email' page. A confirmation email arrives (dev mailbox if SMTP isn't set). | Not run
F-04 | S0 Foundation | Register | Signed out | Try to sign in with the new account before confirming. | Account from F-03 | Sign-in refused with a message to confirm the email, and a link to resend it. | Not run
F-05 | S0 Foundation | Register | New account | Click the confirmation link in the email, then sign in. | - | Email confirmed. After sign-in you land on 'Create business' (no business yet). | Not run
F-06 | S0 Foundation | Create business | New account | Create a business of type Owner. | Name: QA Estates; type Owner | Dashboard opens for QA Estates. Subscription shows a 14-day trial. Credits page shows the trial plan's credits with an 'Allocation' history line. | Not run
F-07 | S0 Foundation | Tenant isolation | owner@ | Open Properties in Acacia Gardens. Switch business to Savanna Homes and open Properties again. | - | Acacia shows Acacia Court and Acacia Shopping Centre only. Savanna shows Savanna Heights only. No data from the other business appears anywhere. | Not run
F-08 | S0 Foundation | Tenant isolation | owner@ | In Acacia Gardens open any invoice and copy its URL. Switch to Savanna Homes and paste the URL. | - | Not found (404). A record from another business can't be opened by URL. | Not run
F-09 | S0 Foundation | Roles | viewer@ | Browse Tenants, Leases, Invoices. Then type /Tenants/Create in the address bar. | - | Lists are readable; no Add/Edit/Record buttons. The create page is refused (access denied). | Not run
F-10 | S0 Foundation | Roles | staff@ | Create a tenant. Then try to open Subscription > Renew, Business settings and Team. | - | Tenant is created. Renew, Business settings and Team are not available to a User. | Not run
F-11 | S0 Foundation | Business switcher | owner@ | Use the switcher at the top of the sidebar to change business. | - | Both businesses listed with their type and role (Owner). Switching changes the business name and data immediately. | Not run
SUB-01 | S1 Subscriptions | Suspended access | lapsed@ | Sign in and try to open Properties. | - | Redirected to the Subscription page: status Suspended, with the payment awaiting approval shown. Other pages aren't reachable. | Not run
SUB-02 | S1 Subscriptions | Approve payment | superadmin@ | Admin > Payment approvals. Approve Lapsed Holdings' payment. | - | Approved. Admin > Businesses shows Lapsed Holdings as Active on Starter. | Not run
SUB-03 | S1 Subscriptions | Access restored | lapsed@ | Sign in again. Open Properties and Credits. | - | Full access. Credits show a plan allocation from the approved renewal. | Not run
SUB-04 | S1 Subscriptions | Plan unit limit | lapsed@ | Properties shows '9 of 10 units used'. Add one unit to Kiprop Flats, then try to add another. | Unit numbers 10, 11 | The 10th unit is added. The 11th is refused with a plan-limit message suggesting an upgrade. | Not run
SUB-05 | S1 Subscriptions | Renewal request | owner@ | Acacia Gardens > Subscription > Renew. Choose a plan and months, M-PESA, enter the code, attach proof. Submit. | Code SJK4H7QX2P; proof: any JPG or PDF | Payment shows as pending verification. | Not run
SUB-06 | S1 Subscriptions | Duplicate code | owner@ | Submit another renewal with the same M-PESA code. | SJK4H7QX2P | Refused: the reference has already been submitted. | Not run
SUB-07 | S1 Subscriptions | Reject payment | superadmin@ | Reject the pending Acacia payment with a reason. | Reason: Code not found on statement | Rejected. The owner sees the reason on the Subscription page and can submit again. | Not run
SUB-08 | S1 Subscriptions | Plans and settings | superadmin@ | Admin > Plans: change Starter's monthly price. Open the public Pricing page. | e.g. +100 | Pricing shows the new price straight away. | Not run
P-01 | S2 Portfolio | Property | owner@ (Acacia) | Properties > Add property. | QA Court; Estate; Nairobi county | Property created and opens on its details page. | Not run
P-02 | S2 Portfolio | Structure | owner@ (Acacia) | Add the structure Block A with Floor 1 and Floor 2. | - | Tree shows QA Court > Block A > Floor 1, Floor 2. | Not run
P-03 | S2 Portfolio | Bulk units | owner@ (Acacia) | Bulk-create units on Block A. | Prefix A, start 1, count 12, Apartment, 2 bed, rent 25,000 | 12 units created, listed in natural order: A1, A2 ... A9, A10, A11, A12 (not A1, A10, A11...). | Not run
P-04 | S2 Portfolio | Unique number | owner@ (Acacia) | Add a single unit numbered A3. | A3 | Refused: unit numbers must be unique within a property. | Not run
P-05 | S2 Portfolio | Unit status rules | owner@ (Acacia) | Try to change unit A5's status to Occupied by hand. | - | Not allowed: Occupied is only set by an active lease. | Not run
P-06 | S2 Portfolio | Portfolio stats | owner@ (Acacia) | Open Properties. | - | Unit count, occupancy %, vacant count and rent roll include QA Court's 12 units. | Not run
P-07 | S2 Portfolio | Delete unit | owner@ (Acacia) | Delete unit A12 (no history). | - | Unit removed from the list. | Not run
T-01 | S3 Tenants and leases | Tenant | owner@ (Acacia) | Tenants > Add tenant. | QA Tenant One; phone 0712 345 678; ID 12345678 | Saved. Phone shows as 0712 345 678 (stored as +254712345678). | Not run
T-02 | S3 Tenants and leases | Documents | owner@ (Acacia) | Upload an ID copy (PDF or JPG) to the tenant. Open it. | Any small PDF/JPG | Listed under documents; opens correctly. | Not run
T-03 | S3 Tenants and leases | Upload safety | owner@ (Acacia) | Rename a .txt file to .pdf and upload it. | fake.pdf | Rejected: the file's content isn't a real PDF. | Not run
T-04 | S3 Tenants and leases | Lease draft | owner@ (Acacia) | Create a lease for QA Tenant One on QA Court A1. | Start: 1st of this month; 12 months; rent 25,000; deposit 25,000; due day 5 | Lease saved as Draft with number L-xxxxx. Unit still Available. | Not run
T-05 | S3 Tenants and leases | Activate | owner@ (Acacia) | Activate the lease. | - | Lease Active; unit A1 shows Occupied. | Not run
T-06 | S3 Tenants and leases | One lease per unit | owner@ (Acacia) | Create a second lease on A1 for another tenant and try to activate it. | Any tenant | Activation refused: the unit already has an active lease. | Not run
T-07 | S3 Tenants and leases | Expiry alerts | owner@ (Acacia) | Open the Dashboard. | - | Leases needing attention include the demo lease ending in about 20 days and the one past its end date. | Not run
T-08 | S3 Tenants and leases | Renewal | owner@ (Acacia) | Renew the lease ending in about 20 days for 12 months at a new rent. | Rent +2,000 | New lease Active, old one Renewed; its charges carried over; unit stays Occupied. | Not run
T-09 | S3 Tenants and leases | Termination | owner@ (Acacia) | Create and activate a lease on QA Court A2, then terminate it today. | Any tenant | Lease ended; unit A2 back to Available (or Inactive if chosen). | Not run
B-01 | S4 Billing | Charges | owner@ (Acacia) | Charges: add a fixed monthly charge, then add it to QA Tenant One's lease (A1). | Parking, 2,000/month | Charge in the library and on the lease. | Not run
B-02 | S4 Billing | Meter readings | owner@ (Acacia) | Readings: enter A1's opening water reading, then this month's reading. | Opening 100; current 112 | Opening isn't billed. Current reading shows 12 units consumed and the charge at the water rate. | Not run
B-03 | S4 Billing | Reading rules | owner@ (Acacia) | Enter a reading lower than the last one; then one dated tomorrow. | 105; tomorrow | Both refused with clear messages. | Not run
B-04 | S4 Billing | Billing run preview | owner@ (Acacia) | Invoices > Generate monthly invoices for this month. Look at the preview. | This month | QA Tenant One shows rent 25,000 + parking 2,000 + water. Demo leases appear too. Nothing is saved yet. | Not run
B-05 | S4 Billing | Generate | owner@ (Acacia) | Generate the invoices. Then run the same month again. | - | Invoices created (INV-xxxxx, Pending). The second run skips every lease already invoiced. Because more than 10 invoices were created, 5 credits are used (see Credits). | Not run
B-06 | S4 Billing | Invoice | owner@ (Acacia) | Open QA Tenant One's invoice. Click Print. | - | Lines and totals correct; due date the 5th. Print view hides the sidebar and menus. | Not run
B-07 | S4 Billing | Proration | owner@ (Acacia) | Create a lease on QA Court A3 starting the 15th of this month and preview its first invoice. | Rent 25,000 | First month's rent is prorated for the days from the 15th. | Not run
B-08 | S4 Billing | Overdue | owner@ (Acacia) | Invoices > Overdue. | - | Last month's unpaid demo invoices (e.g. David, Kwa Njeri) show as Overdue. | Not run
C-01 | S5 Collections | Partial payment | owner@ (Acacia) | Payments > Record payment for QA Tenant One by M-PESA, less than the invoice total. | Code TBA1C2D3E4; amount 10,000 | Preview applies it to the oldest invoice. Receipt RCT-xxxxx created; invoice Partly paid. | Not run
C-02 | S5 Collections | Duplicate code | owner@ (Acacia) | Record another payment with the same code. | TBA1C2D3E4 | Refused: reference already recorded. | Not run
C-03 | S5 Collections | Overpayment | owner@ (Acacia) | Record a payment larger than QA Tenant One's balance. | Cash; balance + 5,000 | Invoice Paid; 5,000 held as credit. Tenant page shows the credit. | Not run
C-04 | S5 Collections | Refund overpayment | owner@ (Acacia) | Refund the 5,000 credit to the tenant. | M-PESA ref of your choice | Refund RFD-xxxxx recorded; credit back to 0. | Not run
C-05 | S5 Collections | Reversal | owner@ (Acacia) | Reverse the cash payment from C-03 with a reason. | Reason: Recorded in error | Receipt shows a REVERSED watermark; the invoice balance is restored. Nothing is deleted. | Not run
C-06 | S5 Collections | Cancel paid invoice | owner@ (Acacia) | Try to cancel an invoice that has a payment on it. | QA Tenant One's invoice | Refused while money is applied to it. | Not run
C-07 | S5 Collections | Statement | owner@ (Acacia) | Open QA Tenant One's statement. Change the date range. | - | Running balance per line, including the reversal and refund. Closing balance equals the balance on the tenant page. | Not run
C-08 | S5 Collections | Deposit refund | owner@ (Acacia) | Try a deposit refund on QA Tenant One's active lease. Then on the ended lease from T-09. | - | Refused on the active lease. Allowed on the ended one, up to the deposit not yet refunded. | Not run
C-09 | S5 Collections | Demo states | owner@ (Acacia) | Payments > Owes money. Open Moses, Mercy and Lucy. | - | David and Kwa Njeri owe money; Moses's cheque shows as reversed; Mercy has credit; Lucy is part-paid. | Not run
A-01 | S6 Arrears, credits, PDFs | Arrears | owner@ (Acacia) | Open Arrears. | - | Overdue split into 1-30, 31-60, 61-90 and 90+ days, by property and by tenant, with collections stage chips. | Not run
A-02 | S6 Arrears, credits, PDFs | Late penalties | owner@ (Acacia) | Late penalties: review the preview, tick some invoices, issue. Open the preview again. | - | Penalty invoices created for the ticked invoices. They no longer appear in the preview (one penalty per invoice). | Not run
A-03 | S6 Arrears, credits, PDFs | Collections notes | owner@ (Acacia) | Open Moses. Add a note with a promised date next week. Then try a promised date in the past. | - | Stage 'Demand served' and timeline visible; new note saved. Past promise date refused. | Not run
A-04 | S6 Arrears, credits, PDFs | Invoice PDF | owner@ (Acacia) | Download an invoice PDF. Open Credits. | - | PDF opens with business details. Balance down 1 credit with a history line. | Not run
A-05 | S6 Arrears, credits, PDFs | Other PDFs | owner@ (Acacia) | Download a receipt PDF and a tenant statement PDF. | - | Both open. Credits down 1 and 2. | Not run
A-06 | S6 Arrears, credits, PDFs | No credits | superadmin@ then owner@ | Admin > Credit purchases > adjust QA Estates' credits to 0 (negative adjustment). As QA Estates' user, download any PDF. | Business # from Admin > Businesses | PDF refused with a message to buy credits. | Not run
A-07 | S6 Arrears, credits, PDFs | Buy credits | owner@ then superadmin@ | Credits > Buy a bundle with a reference. As superadmin, approve it. | Bundle 100; ref QWE1R2T3Y4 | Pending, then approved: balance up by 100 with a Purchase line. | Not run
A-08 | S6 Arrears, credits, PDFs | Health check | Signed out | Open /health. | - | Shows Healthy. | Not run
AC-01 | S7 Accounts and admin | Forgot password | Signed out | Forgot password? for staff@. Open the email link and set a new password. Sign in with it. | New: Qa@654321 | Reset email arrives; password changes; sign-in works with the new password. | Not run
AC-02 | S7 Accounts and admin | Reset link reuse | Signed out | Use the same reset link again. | - | Refused: the link has expired or was already used. | Not run
AC-03 | S7 Accounts and admin | Lockout | Signed out | Enter a wrong password 5 times for viewer@. | - | Account locked for 5 minutes (lockout page). | Not run
AC-04 | S7 Accounts and admin | Unlock | superadmin@ | Admin > Users > viewer@ > Unlock account. Sign in as viewer@. | - | Sign-in works immediately. | Not run
AC-05 | S7 Accounts and admin | Profile | owner@ | Your account > Profile: change name and phone. Save. | Name + ' QA' | Menu shows the new name. The selected business stays selected (no 'Choose a business'). | Not run
AC-06 | S7 Accounts and admin | Password change | owner@ | Your account > Password: change it (then change it back). | - | Changed; you stay in the same business. | Not run
AC-07 | S7 Accounts and admin | Invite member | owner@ (Acacia) | Business settings > Team: invite newuser@ as User. | newuser@smartbiz.test | Invitation listed as waiting; email sent. | Not run
AC-08 | S7 Accounts and admin | Accept invitation | newuser@ | Sign in. Accept the invitation on 'Choose a business' (or via the email link). | - | Lands on Acacia Gardens' dashboard as a User. | Not run
AC-09 | S7 Accounts and admin | Wrong account | staff@ | Open the invitation link from AC-07's email (before or after acceptance) while signed in as staff@. | - | Refused: the invitation was sent to another email. | Not run
AC-10 | S7 Accounts and admin | Owner rules | admin@ (Acacia) | Team: try to invite someone as Owner, and change the owner's role. | - | Owner role not available to an Admin; owner's row can't be changed. | Not run
AC-11 | S7 Accounts and admin | Last owner | owner@ (Acacia) | Team: change your own role to Admin. | - | Refused: a business must keep at least one Owner. | Not run
AC-12 | S7 Accounts and admin | Remove member | owner@ (Acacia) | Remove newuser@. Then, as newuser@, refresh any page. | - | newuser@ loses access to Acacia Gardens. | Not run
AC-13 | S7 Accounts and admin | Logo on PDFs | owner@ (Acacia) | Business settings: upload a PNG logo. Download an invoice PDF. | Any PNG under 2 MB | Logo shows in settings and at the top of the PDF. | Not run
AC-14 | S7 Accounts and admin | Admin users | superadmin@ | Admin > Users: search, send a reset link, try to lock your own account. | - | Actions work; locking yourself is refused. | Not run
AC-15 | S7 Accounts and admin | Admin businesses | superadmin@ | Admin > Businesses. | - | Every business with owner, plan, status, paid-through, members and credits. | Not run
AC-16 | S7 Accounts and admin | Email settings | superadmin@ | Admin > Settings > Email: enter SMTP details and save. Reload. Send a test email. | Your Brevo details | 'Now:' line names your server. Password shows only 'Saved'. Test arrives, or the server's error is shown. | Not run
AG-01 | S8 Agency | Principal view | agent@ | Sign in. Look at the switcher and sidebar. | - | 'Mji Property Agents · Agency · Principal'. Menus: Sales, Agency (Owners, Contracts, Owner remittances, Agents). Dashboard shows an 'Agency, <last month>' panel. | Not run
AG-02 | S8 Agency | Owners | agent@ | Owners: open Grace Mwende. Add a new owner paid by bank without an account number. | - | Grace shows MC-00001 and payout details. New owner refused until bank name and account number are entered. | Not run
AG-03 | S8 Agency | Contracts | agent@ | Contracts list. | - | MC-00001 Grace / Kilimani Heights / 10% / James; MC-00002 Otieno / Westlands Court / 8% / Wanjiru. | Not run
AG-04 | S8 Agency | One contract per property | agent@ | New contract for Grace (draft). Add Kilimani Heights. Activate with no property. | - | Kilimani Heights not offered/refused (already under an active contract). Activation refused without a property. | Not run
AG-05 | S8 Agency | Statement preview | agent@ | Owner remittances (last month) > Prepare Grace Mwende. | - | Collected for owner KES 225,000; deposits held KES 45,000 (A5's new lease); commission KES 22,500; payable KES 202,500. | Not run
AG-06 | S8 Agency | Adjustment | agent@ | Create draft statement. Add a deduction. | Plumbing repair A1, deduct 3,000 | Payable KES 199,500. | Not run
AG-07 | S8 Agency | Approve and pay | agent@ | Approve, then record the payment to Grace. Download the PDF. | Bank; ref FT2610001 | Status Paid with date and reference; adjustments locked. PDF uses 2 credits. | Not run
AG-08 | S8 Agency | Cancel and redo | agent@ | Prepare Otieno Family Trust; create it; cancel with a reason; prepare it again. | Reason: late payment | Collected KES 120,000 (W3 unpaid); commission KES 9,600; payable KES 110,400. After cancelling, the month can be prepared again. | Not run
AG-09 | S8 Agency | Agent commission | agent@ | Owner remittances > Agent commission (last month). | - | James KES 9,000 (40% of 22,500); Wanjiru KES 3,360 (35% of 9,600). | Not run
AG-10 | S8 Agency | Managed-for badge | agent@ | Open the Kilimani Heights property page. | - | Shows 'Managed for Grace Mwende'. | Not run
AG-11 | S8 Agency | Agent view | james@ | Sign in. Look at the menu; open Contracts; paste MC-00002's URL (copied as agent@). | - | Switcher says Agent. Menu shows My contracts, Owners, Owner remittances, My commission (no Agents). Only MC-00001 listed; MC-00002 not found. | Not run
AG-12 | S8 Agency | Agent limits | james@ | On MC-00001: prepare a statement and add an adjustment. Look for Approve and Edit terms. | - | Preparing and adjusting work. No Approve, Edit terms or End buttons; owner records are read-only. | Not run
AG-13 | S8 Agency | Move contracts | agent@ | Agents > James > Move contracts to Wanjiru. As james@, open My contracts. Then move them back. | - | James's list becomes empty, then MC-00001 returns. | Not run
AG-14 | S8 Agency | Unlink login | agent@ then james@ | Edit James: set Login to 'No login'. As james@ refresh. Then relink. | - | Unlinked, James is a normal User and sees all agency contracts; relinked, he's restricted again. | Not run
CO-01 | S9b Development costing | Portfolio | owner@ (Savanna) | Sidebar > Costs and margins. | - | Savanna Heights: expected cost about KES 12.7M, projected margin about 27%. | Not run
CO-02 | S9b Development costing | Project margins | owner@ (Savanna) | Open Savanna Heights > Margins. | - | Budget vs actual grouped by Purchase, Development, Subdivision, Other: Subdivision '+50,000 over'; Infrastructure '600,000 left'. Sales box: 'Sell 4 more units' (fresh database). | Not run
CO-03 | S9b Development costing | Add actual | owner@ (Savanna) | Budget and costs: add an actual Infrastructure cost. | Power connection; 500,000; today | Spent rises by 500,000; expected total unchanged (still within the 3,000,000 budget). | Not run
CO-04 | S9b Development costing | Overspend | owner@ (Savanna) | Add another actual Infrastructure cost. | Extra drainage; 200,000; today | Infrastructure now '+100,000 over'; expected total up by 100,000. | Not run
CO-05 | S9b Development costing | Validation | owner@ (Savanna) | Add an actual cost dated tomorrow; then one with no date. | - | Both refused (future actuals should be budgets). | Not run
CO-06 | S9b Development costing | Unit cost | owner@ (Savanna) | Add an actual Construction cost for Plot 7 only. | Fencing Plot 7; 80,000 | Plot 7's cost shows 'incl. KES 80,000 own costs'; other plots unchanged. | Not run
CO-07 | S9b Development costing | Allocation method | owner@ (Savanna) | Purchase and subdivision: switch 'Spread shared costs' to Equally, then By sale value. Check Margins. | - | Unit costs re-spread accordingly. | Not run
CO-08 | S9b Development costing | Subdivision | owner@ (Savanna) | Purchase and subdivision: create plots, then give Plot 2 a title number. | Plot, start 13, count 2, 450 sqm, 1,500,000; title KAJIADO/KITENGELA/5678/2 | Plots 13-14 added; land in plots and roads/common area recalculated; Plot 2 shows its title. | Not run
CO-09 | S9b Development costing | Rental yield | owner@ (Acacia) | Costs and margins > Acacia Court. | - | Gross yield and payback per flat; 'Rental, last 12 months' shows rent collected, letting costs (300,000) and net yield. Letting costs not in the development total. | Not run
CO-10 | S9b Development costing | Access | agent@ | Look for Costs and margins; then type /Costing. | - | Not in the menu; page says it's for Developer or Owner businesses. | Not run
SA-01 | S9 Sales | Sales list | owner@ (Savanna) | Sales. | - | Plot 1 Completed; Plots 2-3 Active (Plot 2 with an overdue amount); Plots 4-5 Reserved. Totals strip filled. | Not run
SA-02 | S9 Sales | Buyer | owner@ (Savanna) | New sale > 'Add a new buyer'. Save. | QA Buyer; 0722 000 111 | Returns to the sale form with QA Buyer selected. | Not run
SA-03 | S9 Sales | Schedule | owner@ (Savanna) | Choose Plot 6, instalments, 12 monthly. Watch the preview. | - | Price fills 1,450,000; deposit 290,000. Schedule totals exactly 1,450,000; rounding cents on the last instalment. | Not run
SA-04 | S9 Sales | Reserve | owner@ (Savanna) | Record the sale. Open Plot 6's property page and try to change its status. | - | Sale SL-xxxxx Reserved; Plot 6 Reserved; manual status change refused (follows the sale). | Not run
SA-05 | S9 Sales | Payments | owner@ (Savanna) | Record 400,000 by M-PESA. Then try more than the balance; then the same code again. | Code SVQ1W2E3R4 | Deposit paid, instalment 1 partly paid. Overpayment refused. Duplicate code refused. | Not run
SA-06 | S9 Sales | Milestones | owner@ (Savanna) | Record the Agreement (with a PDF). Then Stamp duty and Title transfer. | Title ref KAJIADO/KITENGELA/5678/6 | Only the next step is offered each time. Agreement makes the sale Active and Plot 6 Sold. Documents downloadable. | Not run
SA-07 | S9 Sales | Handover rule | owner@ (Savanna) | Look at the Handover step. | - | Blocked: the buyer must pay in full before handover. | Not run
SA-08 | S9 Sales | Complete | owner@ (Savanna) | Record the remaining balance by bank transfer, then Handover. | Ref FT2610002 | Sale Completed. | Not run
SA-09 | S9 Sales | Reversal | owner@ (Savanna) | Reverse the bank payment. | Reason: Transfer recalled | Sale back to Active; balance restored. | Not run
SA-10 | S9 Sales | Cancel rules | owner@ (Savanna) | Try to cancel Plot 6's sale. Reverse the remaining payment, then cancel. | - | Refused while money is held; then cancelled and Plot 6 Available again. | Not run
SA-11 | S9 Sales | Overdue instalment | owner@ (Savanna) | Open Plot 2 (Ruth). Record a payment equal to the overdue amount. | - | The oldest unpaid instalment is cleared; overdue becomes 0. | Not run
SA-12 | S9 Sales | Reports | owner@ (Savanna) | Sales > Reports. | - | Stock by project; overdue instalments by age (Plot 4's deposit); pipeline (Plots 4, 5); sold units. | Not run
SA-13 | S9 Sales | Buyer statement | owner@ (Savanna) | Download Plot 3's buyer statement PDF. | - | Schedule, payments and balance; 2 credits used. | Not run
SA-14 | S9 Sales | Agency sale | agent@ | Sales > New sale on Kilimani Heights A6 with agent James and 3% commission, full payment. Record 300,000. Open Agent commission and pick THIS month. | Price 6,000,000 | Commission on sales: KES 9,000 commission, James earns KES 3,600. | Not run
SA-15 | S9 Sales | Agent's sales | james@ | Open My sales. | - | Only the A6 sale (assigned to him) is listed. | Not run
M-01 | S10 Marketplace | Public listings | Signed out | Open /properties. | - | Acacia Court flats, Savanna Heights plots and the Kilimani flat (minus any now let or sold). Placeholder images where there are no photos. | Not run
M-02 | S10 Marketplace | Search | Signed out | Try Rent / Buy, county, type, beds and max price. | - | Results filter correctly; the count updates. | Not run
M-03 | S10 Marketplace | Enquiry validation | Signed out | Open a listing. Send an enquiry without ticking consent; then with phone 12345. | - | Both refused with clear messages. | Not run
M-04 | S10 Marketplace | Enquiry | Signed out | Send a valid enquiry on a Savanna plot with your own email. | Your name/phone/email | 'Check your email'. Savanna's Leads page doesn't show it yet. | Not run
M-05 | S10 Marketplace | Verified lead | Signed out, then owner@ (Savanna) | Click the confirmation link. Open Savanna > Leads and Credits. | - | 'Enquiry confirmed'. Owners get a 'New lead' email. Lead shows phone/WhatsApp/email; 10 credits used. | Not run
M-06 | S10 Marketplace | Repeat free | Signed out | Click the link again. Then enquire again on the same plot with the same email and confirm. | - | 'Already confirmed'. The new lead is marked 'Repeat, free'; no credits used. | Not run
M-07 | S10 Marketplace | Locked lead | owner@ (Acacia) | Leads: open Mary Wanjiru's locked lead. | - | Opens; 10 credits used; contact details visible. | Not run
M-08 | S10 Marketplace | Refund | owner@ (Acacia) | Report Brian's lead as fake. Report it again. | Reason: Number doesn't exist | Credits refunded once; the second report is refused. | Not run
M-09 | S10 Marketplace | Create listing | owner@ (Acacia) | Listings > New listing for QA Court A4 to let. Save. Upload 2 JPGs; make the second the cover; publish. | - | Title and price suggested. Published with the chosen cover; visible at /properties. | Not run
M-10 | S10 Marketplace | Photo rules | owner@ (Acacia) | Upload a PDF as a photo. | - | Rejected: photos must be JPG or PNG. | Not run
M-11 | S10 Marketplace | Auto-hide | owner@ (Acacia) | Create and activate a lease on QA Court A4. Check Listings and the public page. | - | Listing shows 'Unit not available'; public page says no longer available; it's gone from search. | Not run
M-12 | S10 Marketplace | Rate limit | Signed out | Send 6 enquiries within 10 minutes from the same browser. | - | The 6th is refused (Too Many Requests). | Not run
M-13 | S10 Marketplace | Home page | Signed out | Open the home page. | - | 'Just listed' shows the 3 newest live listings. | Not run
X-01 | X Cross-cutting | Mobile | owner@ | Chrome DevTools > iPhone SE (375px): sign in, dashboard, record a payment, receipt, /properties. | - | Menu opens as a slide-out; forms usable; wide tables scroll sideways; nothing cut off. | Not run
X-02 | X Cross-cutting | Emails | superadmin@ | Open /dev/mailbox (if SMTP isn't set) or your inbox. | - | Confirmation, reset, invitation, enquiry and lead emails are all present, branded and with working links. | Not run
X-03 | X Cross-cutting | Errors | Any | Open a made-up address, e.g. /Invoices/Details/999999. | - | A friendly not-found page; no stack trace. | Not run
X-04 | X Cross-cutting | Sign out | Any | Sign out, then press Back. | - | You're signed out; protected pages ask you to sign in. | Not run

## Defects
Defect ID | Test ID | Severity | What happened | Steps to reproduce | Expected | Status | Fixed in (zip / date)
EXAMPLE | SA-05 | High | Recording 400,000 showed an error page instead of the receipt. | Savanna Homes > Sales > SL-00006 > Record payment 400,000 M-PESA SVQ1W2E3R4 | Payment recorded; deposit shown as paid | Open